## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BILASPUR Piped Water Supply Scheme | SM/16563 | New | Material Requisition To Resource Division |  |  | RTOR000126/2022-2023 | 632/RD/PHE | 02/03/2023 | 02/03/2023 | Resource Division | 38.8 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BILASPUR Piped Water Supply Scheme | SM/16563 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Bilaspur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018367) | Assistant Engineer - I | Junior Engineer-02 | ORD/000641/2023-2024 | 2738/MLMD | 14/08/2023 | 28/12/2025 | MANIK CHANDRA SAHA. | 26.91 | 0 | 0 | 77
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BILASPUR Piped Water Supply Scheme | SM/16563 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bilaspur PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000455/2024-2025 | 3768/RD/PHED | 18/12/2024 | 01/02/2025 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 19.54 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BILASPUR Piped Water Supply Scheme | SM/16563 | New | Implementation of BILASPUR and its adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000227/2023-2024 | 2406/RD/PHE | 17/08/2023 | 08/04/2025 | M/S ALISA CONSTRUCTION | 303.65 | 0 | 0 | 30
Total | [13 empty] | 388.89 | 0 | 0