## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | CHAPWA PIPED WATER SUPPLY SCHEME at GOALPOKHAR-I BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16647 | New | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 2269/RD | 03/08/2023 | 03/08/2023 | Resource Division | 30.86 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | CHAPWA PIPED WATER SUPPLY SCHEME at GOALPOKHAR-I BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16647 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chapwa Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018401) | Assistant Engineer - I | Junior Engineer-02 | ORD/000593/2023-2024 | 2642/MLMD | 10/08/2023 | 09/06/2026 | ANIMA ENTERPRISE | 27.45 | 0 | 0 | 0
Total | [13 empty] | 58.31 | 0 | 0