## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17199 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 4.59 | 7.29 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17199 | New | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 2249/RD/PHE | 03/08/2023 | 03/08/2023 | Resource Division | 125.79 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17199 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MOHISHGAON PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000507/2023-2024 | 632/RD/PHE | 05/03/2024 | 19/04/2024 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 22.58 | 22.54 | 99.83 | 100
4 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17199 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Mohishgaon, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03546/2023-2024 | BP-2023-24-573 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 5.89 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17199 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Mohishgaon, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03635/2023-2024 | BP-2023-24-619 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.LTD | 8.92 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17199 | New | Implementation of MOHISHGAON and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000012/2023-2024 | 1274/RD/PHE | 08/05/2023 | 24/10/2025 | UTTAM SAHA | 373.39 | 157.07 | 42.07 | 50
7 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17199 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Mohishgaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018892) | Assistant Engineer - I | Junior Engineer-07 | ORD/000688/2023-2024 | 2763/MLMD | 14/08/2023 | 10/02/2024 | UTTAM KUMAR GHOSH | 24.23 | 17.22 | 71.08 | 88
8 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17199 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Mahishgaon PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000435/2024-2025 | 3748/RD/PHE | 18/12/2024 | 02/05/2025 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 21.97 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17199 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Mohishgaon Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity-45 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000302/2025-2026 | 2471/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 19.34 | 0 | 0 | 0
Total | [13 empty] | 665.15 | 201.43 | 30.28