## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sripur Piped Water Supply Scheme | SM/17226 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer RSD |  | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 04/10/2022 | RADIANT | 47.87 | 0.78 | 1.63 | 100
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sripur Piped Water Supply Scheme | SM/17226 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1315/RD/PHE | 12/05/2023 | 12/05/2023 | Resource Division | 6.2 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Sripur Piped Water Supply Scheme | SM/17226 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Source augmentation of Sripur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016135) | Assistant Engineer - I | Junior Engineer-02 | ORD/000441/2023-2024 | 2452/MLMD | 04/08/2023 | 23/03/2026 | SOVA ENTERPRISE. | 6.95 | 5.66 | 81.36 | 81
Total | [13 empty] | 61.02 | 6.44 | 10.55