## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sripur Piped Water Supply Scheme | SM/17226 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer RSD |  | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 04/10/2022 | RADIANT | 47.87 | 0.78 | 1.63 | 100
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sripur Piped Water Supply Scheme | SM/17226 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1315/RD/PHE | 12/05/2023 | 12/05/2023 | Resource Division | 6.2 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Sripur Piped Water Supply Scheme | SM/17226 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Source augmentation of Sripur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016135) | Assistant Engineer - I | Junior Engineer-02 | ORD/000441/2023-2024 | 2452/MLMD | 04/08/2023 | 23/11/2025 | SOVA ENTERPRISE. | 6.95 | 5.66 | 81.36 | 81
4 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sripur Piped Water Supply Scheme | SM/17226 | New | Implementation of Sripur and it's adjoining mouzas Pipe Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House at Head Work Site.) | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000274/2022-2023 | 880/RD/PHE | 27/03/2023 | 23/02/2026 | DONE ENTERPRISE PAPIYABHOWMICK7@GMAIL.COM | 42.48 | 9.42 | 22.17 | 20
5 | UTTAR DINAJPUR | Itahar | Raiganj Division | Sripur Piped Water Supply Scheme | SM/17226 | New | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under SRIPUR PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000496/2023-2024 | 616/RD/PHE | 05/03/2024 | 19/04/2024 | ULKA ENTERPRISE | 5.56 | 0 | 0 | 0
Total | [13 empty] | 109.06 | 15.85 | 14.54