## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/17255 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 4.28 | 6.79 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/17255 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 2250/RD/PHE | 03/08/2023 | 03/08/2023 | Resource Division | 28.77 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/17255 | New | Implementation of SAMASPUR and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division,PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000018/2023-2024 | 1280/RD/PHE | 08/05/2023 | 01/07/2026 | UTTAM SAHA | 418.14 | 220.74 | 52.79 | 35
4 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/17255 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Samaspur, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03656/2023-2024 | BP-2023-24-632 | 06/03/2024 | 06/03/2024 | W.B.S.E.D.C.LTD | 0.56 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/17255 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Samaspur, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03657/2023-2024 | BP-2023-24-633 | 06/03/2024 | 06/03/2024 | W.B.S.E.D.C.LTD | 0.45 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/17255 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer HQ | Estimator | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 28/06/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0.8 | 16.59 | 100
7 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/17255 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Samaspur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/019160) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000692/2023-2024 | 2767/MLMD | 14/08/2023 | 27/04/2026 | M/S TRILOCHAN CONSTRUCTION CO. | 24.39 | 7.81 | 32.03 | 88
8 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/17255 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Samaspur PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000493/2024-2025 | 26/RD/PHE | 02/01/2025 | 16/02/2025 | UTTAM SAHA | 31.62 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/17255 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 12/02/2026 | TECHVISION | 5 | 0 | 0 | 83
Total | [13 empty] | 576.75 | 233.63 | 40.51