## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17256 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 1.13 | 1.78 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17256 | New | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 2236/RD/PHE | 02/08/2023 | 02/08/2023 | Resource Division | 6.43 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17256 | New | Implementation of Balufara Zone-I and it's adjoining mouzas Pipe Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House Head Work.) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000542/2022-2023 | 954/RD/PHE | 29/03/2023 | 01/03/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 88.07 | 46.19 | 52.45 | 50
4 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17256 | New | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under BALUFARA ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000497/2023-2024 | 619/RD/PHE | 05/03/2024 | 19/04/2024 | M/S PRATIMA CHOUDHURY | 5.57 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17256 | New | Requisition of fund regarding payment for permanent restoration of rural roads damaged due to laying of pipeline by PHE Dte. as on 24.09.2024 i.c.w Balufara to Agapur (Package No. WB15198), under coverage of Balufara Zone I PWSS (SM/17256) |  |  | BILL/00476/2024-2025 | BP-2024-25-277 | 08/10/2024 | 08/10/2024 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 1.41 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17256 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Balufara (Zone-I), Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03666/2023-2024 | BP-2023-24-631 | 06/03/2024 | 06/03/2024 | W.B.S.E.D.C.LTD | 0.12 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17256 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Balufara Zone-1 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000487/2024-2025 | 20/RD/PHE | 02/01/2025 | 16/02/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 10.09 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17256 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bahala zone -I PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000490/2024-2025 | 23/RD/PHE | 02/01/2025 | 17/04/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 44.47 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17256 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Balufara (Zone-I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020259) | Assistant Engineer - I | Junior Engineer-07 | ORD/000624/2023-2024 | 2731/MLMD | 14/08/2023 | 21/05/2025 | CHATTERJEE CONSTRUCTION | 7.18 | 5.71 | 79.48 | 100
Total | [13 empty] | 226.39 | 53.03 | 23.42