## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17436 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 3.81 | 6.05 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17436 | New | Implementation of SURANGAPUR (ZONE-II) and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000017/2023-2024 | 1279/RD/PHE | 08/05/2023 | 01/07/2026 | SANYAL ENTERPRISE | 281.07 | 105.61 | 37.58 | 65
3 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17436 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Surangapur Zone- II Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018492) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000801/2023-2024 | 2771/MLMD | 14/08/2023 | 19/10/2025 | PABITRA MANDAL | 24.23 | 18.01 | 74.29 | 88
4 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17436 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Surangapur (Zone-II) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001956/2023-2024 | 4003279058 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 17.09 | 17.09 | 100 | 100
5 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17436 | New | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 2238/RD/PHE | 02/08/2023 | 02/08/2023 | Resource Division | 24.57 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17436 | New | Restoration of Damaged CC Road Near 2nd Tubewell Site of Surangapur Zone-II Water Supply Scheme (New Scheme) at Hemtabad Block Under Raiganj Division P.H.E Dte. | Assistant Engineer RSD |  | ORD/000125/2024-2025 | 3016/RD/PHE | 03/10/2024 | 23/10/2024 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 3.24 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17436 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SURANGAPUR ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000553/2023-2024 | 650/RD/PHE | 05/03/2024 | 19/04/2024 | CHAITANYA SAMAL | 11.29 | 11.07 | 98.07 | 100
8 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17436 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SURANGAPUR ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000552/2023-2024 | 649/RD/PHE | 05/03/2024 | 19/04/2024 | SAHA CONSTRUCTION SAHAKUMARESH51@GMAIL.COM | 11.29 | 11.25 | 99.66 | 100
9 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17436 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Surangapur PWSS (Zone-II), Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02459/2023-2024 | BP-2023-24-399 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 7.51 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17436 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Surangapur Zone II PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000470/2024-2025 | 03/RD/PHE | 02/01/2025 | 16/02/2025 | SANYAL ENTERPRISE | 42.37 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17436 | New | Trial Run For Surangapur Zone-II PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000683/2024-2025 | 531/RD/PHE | 12/02/2025 | 13/05/2025 | SANYAL ENTERPRISE | 0.88 | 0 | 0 | 0
Total | [13 empty] | 486.58 | 166.85 | 34.29