## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17437 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 2.51 | 3.98 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17437 | New | Implementation of SURANGAPUR (ZONE-III) and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000083/2023-2024 | 1995/RD/PHE | 13/07/2023 | 08/04/2024 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 164.11 | 81.07 | 49.4 | 50
3 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17437 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Surangapur (Zone-III) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018494) | Assistant Engineer - I,Assistant Engineer - II | Junior Engineer-07 | ORD/000611/2023-2024 | 2725/MLMD | 14/08/2023 | 10/02/2024 | S.G.ENTERPRISE | 7.17 | 7.14 | 99.59 | 100
4 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17437 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 2239/RD/PHE | 02/08/2023 | 02/08/2023 | Resource Division | 11.53 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17437 | New | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under SURANGAPUR ZONE-III PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000517/2023-2024 | 648/RD/PHE | 05/03/2024 | 19/04/2024 | M/S ARITRA DUTTA | 5.56 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17437 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Surangapur (Zone-III), Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/00207/2024-2025 | BP-2024-25-74 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 0.14 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17437 | New | Approach road with land development of headwork site and road restoration of Surangapur zone III PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000472/2024-2025 | 05/RD/PHE | 02/01/2025 | 16/02/2025 | M/S ROYAL CONSTRUCTION | 5.7 | 0 | 0 | 0
Total | [13 empty] | 257.25 | 90.72 | 35.26