## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/17631 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 1045/RD/PHE | 05/04/2023 | 05/04/2023 | Resource Division | 30.48 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/17631 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 26/08/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 19.35 | 0.15 | 35
3 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/17631 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 05/10/2024 | SISIR KUMAR DUTTA | 4.8 | 0.05 | 1.1 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/17631 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Baligora Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000279/2025-2026 | 1799/RD/PHE | 24/06/2025 | 21/12/2025 | AJIT PRAMANIK | 29.58 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/17631 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Baligora Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/003985) | Assistant Engineer - I | Junior Engineer-02 | ORD/000395/2023-2024 | 2435/MLMD | 04/08/2023 | 26/06/2026 | SOUNAK ENTERPRISE | 26.22 | 0 | 0 | 72
6 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/17631 | New | Land Development and Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for Baligora PWSS under Islampur Sub-Division PHED under Raiganj Division, PHED.,U/D. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000373/2025-2026 | 2280/RD/PHE | 11/08/2025 | 09/12/2025 | MILAN GHOSH | 1.95 | 0 | 0 | 0
Total | [13 empty] | 13024.11 | 19.4 | 0.15