## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. | SM/17742 | Augmentation | Preparation of DPR for drinking water supply scheme to facilitate 4(Four)Nos. Augmentation Scheme and 1(One) No. New PWSS (List Enclosed) Uncovered mouzas under Uttar Dinajpur District which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000201/2023-2024 | 2226/RD/PHE | 31/07/2023 | 15/08/2023 | RADIANT | 11.57 | 0 | 0 | 100
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. | SM/17742 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 1104/RD/PHE | 20/04/2023 | 20/04/2023 | Resource Division | 4.6 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. | SM/17742 | Augmentation | Augmentation of Sergram and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000523/2022-2023 | 883/RD/PHE | 27/03/2023 | 16/03/2025 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 88.22 | 0 | 0 | 45
4 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. | SM/17742 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Shergram, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03667/2023-2024 | BP-2023-24-630 | 06/03/2024 | 06/03/2024 | W.B.S.E.D.C.LTD | 0.12 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. | SM/17742 | Augmentation | Additional quotation for energization at TW No-III of Shergram water supply scheme in the district of Uttar Dinajpur. |  |  | BILL/01449/2024-2025 | BP-2024-25-359 | 04/07/2024 | 04/07/2024 | W.B.S.E.D.C.LTD | 3.84 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. | SM/17742 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Augmentation of Shergram Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018651) | Assistant Engineer - I | Junior Engineer-07 | ORD/000609/2023-2024 | 2724/MLMD | 14/08/2023 | 10/02/2024 | JOY MAA SANTOSHI ENTERPRISE. | 7.18 | 0 | 0 | 100
Total | [13 empty] | 115.53 | 0 | 0