## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18147 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 3314/RD/PHE | 05/12/2023 | 05/12/2023 | Resource Division | 3.25 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18147 | New | Implementation of PASCHIM GAGRA and it's adjoining mouzas Pipe Water Supply Scheme at KALIAGANJ Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000052/2023-2024 | 1559/RD/PHE | 29/05/2023 | 27/08/2023 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 59.46 | 30.28 | 50.93 | 61
3 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18147 | New | Approach road with land development of headwork site & 2nd tubewell site and road restoration of Paschim Gagra PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000464/2024-2025 | 3782/RD/PHE | 19/12/2024 | 02/02/2025 | DAS CONSTRUCTION COMPANY | 5.78 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18147 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Paschim Gagara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020864) | Assistant Engineer - I | Junior Engineer-07 | ORD/001669/2023-2024 | 2700/MLMD | 11/08/2023 | 01/01/2025 | M/S JIBU SINGHA | 7.18 | 7.15 | 99.58 | 100
5 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18147 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Paschim Gagara, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/00206/2024-2025 | BP-2024-25-73 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 0.14 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18147 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Paschim Gagra Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 10 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000345/2025-2026 | 2492/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 13.83 | 0 | 0 | 0
Total | [13 empty] | 89.63 | 37.43 | 41.76