## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18148 | New | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 2266/RD/PHE | 03/08/2023 | 03/08/2023 | Resource Division | 15.02 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18148 | New | Implementation of DAKSHINAL and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RWS,Junior Engnieer, RWS(HQ) | ORD/000226/2023-2024 | 2385/RD/PHE | 16/08/2023 | 03/12/2025 | MILAN DEBNATH | 215.59 | 74.42 | 34.52 | 25
3 | UTTAR DINAJPUR | Itahar | Malda Mechanical | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18148 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. I & II of Dakshinal Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020903) | Assistant Engineer - I | Junior Engineer-02 | ORD/002029/2023-2024 | 4768/MLMD | 29/12/2023 | 16/06/2026 | M/S S. S. ENTERPRISE | 21.07 | 0 | 0 | 84
4 | UTTAR DINAJPUR | Itahar | Raiganj Division | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18148 | New | Construction of Approach Road,Laying of Pipe Line,Fhtc and Other Allied Works Of Dakshinal Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000395/2024-2025 | 3564/RD/PHE | 05/12/2024 | 14/08/2025 | M/S. DEBNATH ENTERPRISE | 41.36 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Itahar | Raiganj Division | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18148 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakshinal Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 30 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000319/2025-2026 | 2479/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 17.34 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Itahar | Raiganj Division | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18148 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DAKSHINAL PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000538/2023-2024 | 625/RD/PHE | 05/03/2024 | 21/04/2025 | DULAL MAJUMDER | 11.29 | 0 | 0 | 100
7 | UTTAR DINAJPUR | Itahar | Raiganj Division | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18148 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DAKSHINAL PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000537/2023-2024 | 624/RD/PHE | 05/03/2024 | 24/04/2025 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. | 11.29 | 0 | 0 | 100
8 | UTTAR DINAJPUR | Itahar | Raiganj Division | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18148 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59C 0644) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 01/07/2024 to 14/01/2025. | Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RWS | ORD/000407/2024-2025 | 1980/RD/PHE | 29/06/2024 | 13/01/2025 | PRITAM SARKAR | 2.6 | 0.4 | 15.38 | 100
Total | [13 empty] | 335.57 | 74.82 | 22.3