## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Chopra | Raiganj Division | DAKSHIN DAMORGACHH PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR. | SM/18149 | New | Implementation of DAKSHIN DAMODARGACHH and it's adjoining mouzas Pipe Water Supply Scheme at CHOPRA Block of Uttar Dinajpur District under Raiganj Division. (Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections & Pump House.) | Assistant Engineer ISD | Junior Engineer,Junior Engineer, ISD | ORD/000048/2023-2024 | 1555/RD/PHE | 29/05/2023 | 23/11/2025 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 81.37 | 41.93 | 51.53 | 50
2 | UTTAR DINAJPUR | Chopra | Malda Mechanical | DAKSHIN DAMORGACHH PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR. | SM/18149 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. I & II of Dakshin Damorgachh Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020855) | Assistant Engineer - I | Junior Engineer-02 | ORD/000730/2023-2024 | 4776/MLMD | 29/12/2023 | 26/06/2024 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 14.41 | 11.74 | 81.48 | 82
3 | UTTAR DINAJPUR | Chopra | Raiganj Division | DAKSHIN DAMORGACHH PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR. | SM/18149 | New | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 2271/RD | 03/08/2023 | 03/08/2023 | Resource Division | 6.79 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Chopra | Raiganj Division | DAKSHIN DAMORGACHH PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR. | SM/18149 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DAKSHIN DAOMODARGACHH PWSS at Chopra Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer,Junior Engineer, ISD | ORD/000050/2024-2025 | 1709/RD/PHE | 10/06/2024 | 07/03/2025 | FIZA CONSTRUCTION | 10.19 | 9.49 | 93.09 | 100
5 | UTTAR DINAJPUR | Chopra | Raiganj Division | DAKSHIN DAMORGACHH PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR. | SM/18149 | New | Additional pipeline, Pathway, Land Development and other ancillary works at Dakshin Damodargachh Piped Water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000397/2025-2026 | 1596/RD/PHE | 16/06/2025 | 14/10/2025 | SANDIP SARKAR | 12.06 | 0 | 0 | 0
Total | [13 empty] | 124.83 | 63.16 | 50.6