## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | MAHADIPUR MINI PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18155 | New | Implementation of MAHADIPUR Mini Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD | ORD/000054/2023-2024 | 1561/RD/PHE | 29/05/2023 | 27/08/2023 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 58.48 | 0 | 0 | 20
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | MAHADIPUR MINI PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18155 | New | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 2254/RD/PHE | 03/08/2023 | 03/08/2023 | Resource Division | 5.67 | 0 | 0 | 0
Total | [13 empty] | 64.15 | 0 | 0