## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | LOHANDA PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18159 | New | Implementation of LOHANDA and its adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000020/2023-2024 | 1282/RD/PHE | 08/05/2023 | 03/05/2026 | BHOLA PAUL | 135.29 | 72.22 | 53.38 | 50
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | LOHANDA PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18159 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II of Lohanda Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020859) | Assistant Engineer - I | Junior Engineer-07 | ORD/002027/2023-2024 | 4766/MLMD | 29/12/2023 | 26/06/2024 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 19.98 | 16.48 | 82.46 | 82
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | LOHANDA PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18159 | New | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 2262/RD/PHE | 03/08/2023 | 03/08/2023 | Resource Division | 10.97 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | LOHANDA PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18159 | New | Construction of Boundary Wall With Gate at Head Work & 2nd Tube-Well Site under LOHANDA PWSS at Raiganj Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000505/2023-2024 | 628/RD/PHE | 05/03/2024 | 01/03/2025 | M/S MANDAL ENTERPRISE | 11.14 | 3.93 | 35.34 | 48
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | LOHANDA PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18159 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Lohanda PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000484/2024-2025 | 17/RD/PHE | 02/01/2025 | 01/02/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 11.25 | 0 | 0 | 0
Total | [13 empty] | 188.62 | 92.63 | 49.11