## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR | SM/18160 | New | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 2263/RD/PHE | 03/08/2023 | 03/08/2023 | Resource Division | 14.12 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR | SM/18160 | New | Construction of Approach Road,Laying of Pipe Line,Fhtc and other Allied Works of Hasua Pwss within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000393/2024-2025 | 3563/RD/PHE | 05/12/2024 | 19/01/2025 | M/S SARKAR ENTERPRISE | 47.11 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Itahar | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR | SM/18160 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 15.07.2024 to 16.07.2024 and from 18.07.2024 to 19.07.2024. |  |  | BILL/00274/2024-2025 | BP-2024-25-181 | 30/08/2024 | 30/08/2024 | M/S DILWAR HOSAIN | 0.08 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Itahar | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR | SM/18160 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer HQ | Estimator | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 28/06/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
5 | UTTAR DINAJPUR | Itahar | Malda Mechanical | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR | SM/18160 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. I & II of Hasua Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020862) | Assistant Engineer - I | Junior Engineer-02 | ORD/000729/2023-2024 | 2709/MLMD | 11/08/2023 | 26/06/2026 | MUKHERJEE ART CENTRE | 20.41 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Itahar | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR | SM/18160 | New | Implementation of HASUA and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD ,Junior Engineer, RWS,Junior Engnieer, RWS(HQ) | ORD/000376/2023-2024 | 2600/RD/PHE | 13/09/2023 | 02/10/2025 | M/S EVEREST INFRATECH INC | 220.85 | 71.34 | 32.3 | 45
7 | UTTAR DINAJPUR | Itahar | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR | SM/18160 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under HASUA PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000502/2023-2024 | 623/RD/PHE | 05/03/2024 | 19/04/2024 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 24.48 | 0 | 0 | 40
8 | UTTAR DINAJPUR | Itahar | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR | SM/18160 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Hasua Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 30 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000320/2025-2026 | 2480/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 17.34 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Itahar | Malda Mechanical | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR | SM/18160 | New | Quotation for new service connection at HASUA PH-I (Itahar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18160) |  |  | BILL/02971/2024-2025 | BP-2024-25-631 | 06/02/2025 | 06/02/2025 | W.B.S.E.D.C.LTD | 4.21 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Itahar | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR | SM/18160 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59C 0644) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 01/07/2024 to 14/01/2025. | Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RWS | ORD/000407/2024-2025 | 1980/RD/PHE | 29/06/2024 | 13/01/2025 | PRITAM SARKAR | 2.6 | 0.4 | 15.38 | 100
Total | [13 empty] | 356.01 | 71.74 | 20.15