## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18164 | New | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 2265/RD/PHE | 03/08/2023 | 03/08/2023 | Resource Division | 11.63 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18164 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II of Krishnapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020850) | Assistant Engineer - I | Junior Engineer-07 | ORD/002026/2023-2024 | 4765/MLMD | 29/12/2023 | 26/06/2024 | JOY MAA SANTOSHI ENTERPRISE. | 19.99 | 15 | 75.03 | 82
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18164 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KRISNAPUR PWSS at Raiganj Block under Raiganj Division,PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000503/2023-2024 | 626/RD/PHE | 05/03/2024 | 19/04/2024 | M/S UNIQUE 13 | 10.26 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18164 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Krishnapur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/00750/2024-2025 | BP-2024-25-209 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 1.13 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18164 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Krishnapur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/00749/2024-2025 | BP-2024-25-208 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 3.18 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18164 | New | Demand for placing necessary fund for the work of Permanent restoration of damaged hard shoulder/flank caused due pipe laying by PHE Department under Krishnapur PWSS at a stretches of Thakurbari-Bindol road under Uttar Dinajpur Highway Division, PWD (Roads) Dte. |  |  | BILL/00119/2024-2025 | BP-2024-25-83 | 18/06/2024 | 18/06/2024 | EXECUTIVE ENGINEER PWD ROADS | 10.34 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18164 | New | Implementation of KRISHNAPUR and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000084/2023-2024 | 1996/RD/PHE | 13/07/2023 | 02/04/2025 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 135.44 | 15.83 | 11.69 | 55
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18164 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Krishnapur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000447/2024-2025 | 3759/RD/PHED | 18/12/2024 | 02/05/2025 | ANILA CONSTRUCTION | 11.51 | 0 | 0 | 0
Total | [13 empty] | 203.47 | 30.83 | 15.15