## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Chopra | Raiganj Division | BINAPUR PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18165 | New | Implementation of BINAPUR and it's adjoining mouzas Pipe Water Supply Scheme at CHOPRA Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | Assistant Engineer ISD |  | ORD/000229/2023-2024 | 2378/RD/PHE | 14/08/2023 | 12/11/2023 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 53.95 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Chopra | Raiganj Division | BINAPUR PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18165 | New | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 3315/RD/PHE | 05/12/2023 | 05/12/2023 | Resource Division | 4.8 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Chopra | Malda Mechanical | BINAPUR PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18165 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Binapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020936) | Assistant Engineer - I | Junior Engineer-02 | ORD/001670/2023-2024 | 2706/MLMD | 11/08/2023 | 23/11/2026 | M/S JIBU SINGHA | 7.2 | 0 | 0 | 0
Total | [13 empty] | 65.95 | 0 | 0