## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18167 | New | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 2257/RD/PHE | 03/08/2023 | 03/08/2023 | Resource Division | 6.26 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18167 | New | Implementation of BANKUR and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD | ORD/000050/2023-2024 | 1557/RD/PHE | 29/05/2023 | 27/08/2023 | UTTAM SAHA | 84.34 | 0 | 0 | 55
3 | UTTAR DINAJPUR | Itahar | Malda Mechanical | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18167 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. I & II of Bankur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020973) | Assistant Engineer - I | Junior Engineer-02 | ORD/000728/2023-2024 | 2708/MLMD | 11/08/2023 | 26/06/2026 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 14.28 | 0 | 0 | 69
4 | UTTAR DINAJPUR | Itahar | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18167 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 29.07.2024 to 02.08.2024. |  |  | BILL/00275/2024-2025 | BP-2024-25-180 | 30/08/2024 | 30/08/2024 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Itahar | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18167 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 01.07.2024 to 05.07.2024. |  |  | BILL/00232/2024-2025 | BP-2024-25-155 | 30/07/2024 | 30/07/2024 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Itahar | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18167 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 08.07.2024 to 12.07.2024. |  |  | BILL/00231/2024-2025 | BP-2024-25-156 | 30/07/2024 | 30/07/2024 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Itahar | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18167 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bankur Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 10 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000348/2025-2026 | 2494/RD/PHE | 12/09/2025 | 11/03/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.82 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Itahar | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18167 | New | Construction Of Approach Road,Laying Of Pipe Line And Other Allied Works Of Bankur Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000401/2024-2025 | 3570/RD/PHE | 05/12/2024 | 04/01/2025 | UTTAM SAHA | 11.15 | 0 | 0 | 0
Total | [13 empty] | 130.15 | 0 | 0