## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18169 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 2255/RD/PHE | 03/08/2023 | 03/08/2023 | Resource Division | 3.42 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18169 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dhabail, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/00747/2024-2025 | BP-2024-25-207 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 3.05 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18169 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Dhabail Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020919) | Assistant Engineer - I | Junior Engineer-07 | ORD/000721/2023-2024 | 2702/MLMD | 11/08/2023 | 01/03/2025 | SOVA ENTERPRISE. | 7.17 | 0 | 0 | 100
Total | [13 empty] | 13.64 | 0 | 0