## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18169 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 2255/RD/PHE | 03/08/2023 | 03/08/2023 | Resource Division | 3.42 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18169 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dhabail, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/00747/2024-2025 | BP-2024-25-207 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 3.05 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18169 | New | Implementation of DHABAIL and it's adjoining mouzas Pipe Water Supply Scheme at KALIAGANJ Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000051/2023-2024 | 1558/RD/PHE | 29/05/2023 | 23/06/2024 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 57.44 | 49.09 | 85.46 | 85
4 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18169 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Dhabail Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020919) | Assistant Engineer - I | Junior Engineer-07 | ORD/000721/2023-2024 | 2702/MLMD | 11/08/2023 | 01/03/2025 | SOVA ENTERPRISE. | 7.17 | 5.72 | 79.7 | 100
Total | [13 empty] | 71.08 | 54.8 | 77.1