## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | BHARATPUR PIPED WATER SUPPLY SCHEME IN HEMTABAD BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18170 | New | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 2256/RD/PHE | 03/08/2023 | 03/08/2023 | Resource Division | 5.9 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | BHARATPUR PIPED WATER SUPPLY SCHEME IN HEMTABAD BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18170 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I & II of Bharatpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020865) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000716/2023-2024 | 2701/MLMD | 11/08/2023 | 26/04/2026 | SUBRATA KUMAR DAS. | 14.25 | 0 | 0 | 79
3 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | BHARATPUR PIPED WATER SUPPLY SCHEME IN HEMTABAD BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18170 | New | Implementation of BHARATPUR and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000049/2023-2024 | 1556/RD/PHE | 29/05/2023 | 16/08/2025 | BHOLA PAUL | 92.43 | 0 | 0 | 50
4 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | BHARATPUR PIPED WATER SUPPLY SCHEME IN HEMTABAD BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18170 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000410/2024-2025 | 1746/RD/PHE | 14/06/2024 | 29/12/2024 | DEBASISH GHOSH | 2.6 | 0 | 0 | 0
Total | [13 empty] | 115.18 | 0 | 0