## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Khalsi Piped Water Supply Scheme. | SM/18179 | New | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 1332/RD/PHE | 15/05/2023 | 15/05/2023 | Resource Division | 41.2 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Khalsi Piped Water Supply Scheme. | SM/18179 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II of Khalshi Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/004009) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/002476/2023-2024 | 100/MLMD | 11/01/2024 | 09/07/2024 | R. S. ENTERPRISE | 23.44 | 11.51 | 49.09 | 47
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Khalsi Piped Water Supply Scheme. | SM/18179 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Khalsi, 2.Dwipnagar in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000033/2023-2024 | 1490/RD/PHE | 17/05/2023 | 01/07/2023 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 52.73 | 50.74 | 96.24 | 90
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Khalsi Piped Water Supply Scheme. | SM/18179 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Khalsi,, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03526/2023-2024 | BP-2023-24-546 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 0.75 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Khalsi Piped Water Supply Scheme. | SM/18179 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Khalsi, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/00732/2024-2025 | BP-2024-25-184 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 1.85 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Khalsi Piped Water Supply Scheme. | SM/18179 | New | Implementation of KHALSI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000004/2023-2024 | 1129/RD/PHE | 24/04/2023 | 09/05/2026 | SANYAL ENTERPRISE | 386.06 | 54.54 | 14.13 | 50
Total | [13 empty] | 506.03 | 116.79 | 23.08