## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Dwipnagar Piped Water Supply Scheme. | SM/18180 | New | Material Requisition To Resource Division |  |  | RTOR000135/2022-2023 | 653/RD/PHE | 03/03/2023 | 03/03/2023 | Resource Division | 77.81 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Dwipnagar Piped Water Supply Scheme. | SM/18180 | New | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 1330/RD/PHE | 15/05/2023 | 15/05/2023 | Resource Division | 77.13 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Dwipnagar Piped Water Supply Scheme. | SM/18180 | New | Implementation of DWIPNAGAR and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000006/2023-2024 | 1133/RD/PHE | 24/04/2023 | 01/07/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 374.36 | 66.25 | 17.7 | 50
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Dwipnagar Piped Water Supply Scheme. | SM/18180 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Khalsi, 2.Dwipnagar in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000033/2023-2024 | 1490/RD/PHE | 17/05/2023 | 01/07/2023 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 52.73 | 0 | 0 | 90
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Dwipnagar Piped Water Supply Scheme. | SM/18180 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dwipnagar, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03533/2023-2024 | BP-2023-24-553 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 3.3 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Dwipnagar Piped Water Supply Scheme. | SM/18180 | New | Additional Quotation of Dwipnagar TW-II in the district of Uttar Dinajpur. |  |  | BILL/01683/2024-2025 | BP-2024-25-413 | 30/07/2024 | 30/07/2024 | W.B.S.E.D.C.LTD | 4.03 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Dwipnagar Piped Water Supply Scheme. | SM/18180 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Dwipnagar, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03532/2023-2024 | BP-2023-24-552 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 5.62 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Dwipnagar Piped Water Supply Scheme. | SM/18180 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II of Dwipnagar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/004005) | Assistant Engineer - I | Junior Engineer-07 | ORD/000407/2023-2024 | 2440/MLMD | 04/08/2023 | 27/10/2025 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 22.38 | 11.14 | 49.78 | 100
Total | [13 empty] | 617.36 | 77.39 | 12.54