## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | Palaibari Piped Water Supply Scheme. | SM/18181 | New | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 1331/RD/PHE | 15/05/2023 | 15/05/2023 | Resource Division | 44.22 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | Palaibari Piped Water Supply Scheme. | SM/18181 | New | Implementation of PALAIBARI and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000003/2023-2024 | 1128/RD/PHE | 24/04/2023 | 26/12/2025 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 555.91 | 146 | 26.26 | 50
3 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Palaibari Piped Water Supply Scheme. | SM/18181 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no.I, II & III and making compound lighting arrangement at T/W no.I of PALAIBARI Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/002489/2023-2024 | 813/MLMD | 15/02/2024 | 13/08/2024 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 40.02 | 33.41 | 83.47 | 83
4 | UTTAR DINAJPUR | Itahar | Raiganj Division | Palaibari Piped Water Supply Scheme. | SM/18181 | New | Balance work of sinking Rig bored Tube-Well in connection with 2nd and 3rd Tube-Well site due to non-availability of water at the shallow depth of Tube-Well under Palaibari PWSS(New Scheme) at Itahar Block, Raiganj Division ,PHE Dte. | Assistant Engineer RSD |  | ORD/000135/2024-2025 | 3025/RD/PHE | 03/10/2024 | 02/11/2024 | M/S SARKAR ENTERPRISE SILIGURI | 18.33 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Itahar | Raiganj Division | Palaibari Piped Water Supply Scheme. | SM/18181 | New | Arrangement for erection of display board for different piped water supply schemes (1.Palaibari PWSS, 2.Bhomra PWSS, 3.Chandgaon PWSS) under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. |  |  | BILL/00421/2024-2025 | BP-2024-25-271 | 07/10/2024 | 07/10/2024 | M/S MANDAL ENTERPRISE | 0.1 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Itahar | Raiganj Division | Palaibari Piped Water Supply Scheme. | SM/18181 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Palaibari, 2.Kashimpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000032/2023-2024 | 1491/RD/PHE | 17/05/2023 | 22/03/2025 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 57.19 | 25.24 | 44.13 | 80
Total | [13 empty] | 715.77 | 204.64 | 28.59