## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kashimpur Piped Water Supply Scheme. | SM/18182 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1333/RD/PHE | 15/05/2023 | 15/05/2023 | Resource Division | 36.1 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Kashimpur Piped Water Supply Scheme. | SM/18182 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Kashimpur, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/00208/2024-2025 | BP-2024-25-71 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 3.37 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Kashimpur Piped Water Supply Scheme. | SM/18182 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Kashimpur, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/00209/2024-2025 | BP-2024-25-72 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 7 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kashimpur Piped Water Supply Scheme. | SM/18182 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Palaibari, 2.Kashimpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000032/2023-2024 | 1491/RD/PHE | 17/05/2023 | 22/03/2025 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 57.19 | 0 | 0 | 80
5 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kashimpur Piped Water Supply Scheme. | SM/18182 | New | Implementation of KASHIMPUR and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000005/2023-2024 | 1132/RD/PHE | 24/04/2023 | 08/04/2026 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 407.34 | 92.62 | 22.74 | 55
6 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kashimpur Piped Water Supply Scheme. | SM/18182 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kashimpur Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000306/2025-2026 | 2473/RD/PHE | 12/09/2025 | 11/03/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.36 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Kashimpur Piped Water Supply Scheme. | SM/18182 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II of Kashimpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/003990) | Assistant Engineer - I | Junior Engineer-07 | ORD/000423/2023-2024 | 2446/MLMD | 04/08/2023 | 01/01/2025 | DEB CONSTRUCTION. | 22.84 | 5.76 | 25.2 | 100
Total | [13 empty] | 566.19 | 98.38 | 17.38