## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. | SM/18227 | Augmentation | [PART-A]Sinking of Ground Bored Replacement Tube Wells by Direct Rotary Rig method using 300mm diameter x 200mm diameter,250 Mtr. deep Tube Well with 200mm dia UPVC Medium Well Screen (RMS) Pipes with Ribs Strainer 30 Mtr. long having 300mm dia, 45m long UPVC housing pipe, 200mm dia 175m long Well pipe along with 3mtr blank pipe all complete including cost of material with proper development and necessary yield for Islampur S.D.Hospital, Uttar Dinajpur under Raiganj Division, PHED. [PART-B] Laying of Rising Main pipeline including interconnection of Replacement Tubewells for Islampur S.D. Hospital at Islampur Block under Raiganj Division, P.H.E Dte.,Uttar Dinajpur | Assistant Engineer ISD |  | ORD/000443/2021-2022 | 2336/RD/PHE | 16/12/2021 | 15/01/2022 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 14.45 | 12.15 | 84.04 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. | SM/18227 | Augmentation | GROUND BORED BIG DIA TUBE WELL FOR KALIAGANJ MUNICIPAL ZONE-I WSS |  |  | ORD/000307/2019-2020 | 156/RD | 04/02/2020 | 02/02/2026 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 8.01 | 0.08 | 1.01 | 100
3 | UTTAR DINAJPUR |  | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. | SM/18227 | Augmentation | GROUND BORED BIG DIA TUBE WELL FOR KUNOR WSS |  |  | ORD/000304/2019-2020 | 157/RD | 04/02/2020 | 02/02/2026 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 8.64 | 0.51 | 5.87 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. | SM/18227 | Augmentation | SINKING GROUND BORED REPLACEMENT OF ISLAMPUR ZONE-II PWSS |  |  | ORD/000471/2019-2020 | 155/RD | 04/02/2020 | 04/05/2020 | SAMIRAN PODDAR | 13.96 | 0.44 | 3.16 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. | SM/18227 | Augmentation | Replacement of 250 x150mm dia. Tube-Well 250mtr. deep Rig bored Tube-Well for Pokheria PWSS at Itahar Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000443/2023-2024 | 199/RD/PHE | 25/01/2024 | 14/02/2024 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 12.89 | 5.84 | 45.29 | 100
Total | [13 empty] | 57.96 | 19.02 | 32.81