## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. | SM/18227 | Augmentation | GROUND BORED BIG DIA TUBE WELL FOR KALIAGANJ MUNICIPAL ZONE-I WSS |  |  | ORD/000307/2019-2020 | 156/RD | 04/02/2020 | 04/02/2026 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 8.01 | 0.08 | 1.01 | 100
2 | UTTAR DINAJPUR |  | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. | SM/18227 | Augmentation | GROUND BORED BIG DIA TUBE WELL FOR KUNOR WSS |  |  | ORD/000304/2019-2020 | 157/RD | 04/02/2020 | 04/02/2026 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 8.64 | 0.51 | 5.87 | 100
3 | UTTAR DINAJPUR |  | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. | SM/18227 | Augmentation | SINKING GROUND BORED REPLACEMENT OF ISLAMPUR ZONE-II PWSS |  |  | ORD/000471/2019-2020 | 155/RD | 04/02/2020 | 04/05/2020 | SAMIRAN PODDAR | 13.96 | 0.44 | 3.16 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. | SM/18227 | Augmentation | Replacement of 250 x150mm dia. Tube-Well 250mtr. deep Rig bored Tube-Well for Pokheria PWSS at Itahar Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000443/2023-2024 | 199/RD/PHE | 25/01/2024 | 14/02/2024 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 12.89 | 11.68 | 90.59 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. | SM/18227 | Augmentation | Sinking of Ground Bored Replacement Tube-Well 250mm x 150mm dia. of 180 mtr. Direct Rotary Rig Method at Ghirnigaon Khas TW Site under Raiganj Division, P.H.E Dte.(SM/18227) | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000519/2024-2025 | 71/RD/PHE | 06/01/2025 | 05/02/2025 | M/S SARKAR ENTERPRISE SILIGURI | 10.69 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. | SM/18227 | Augmentation | Replacement for Replacement Tube-Well & Inter Connection in connection With Head Work Site of Phulatti PWSS under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000520/2024-2025 | 72/RD/PHE | 06/01/2025 | 05/02/2025 | M/S SARKAR ENTERPRISE SILIGURI | 11.35 | 0 | 0 | 0
Total | [13 empty] | 65.54 | 12.71 | 19.39