## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Raiganj Division | TOPAMARI PWSS | SM/18243 | New | Material Requisition To Resource Division |  |  | RTOR000113/2022-2023 | 602/RD/PHE | 27/02/2023 | 27/02/2023 | Resource Division | 57.96 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Islampur | Malda Mechanical | TOPAMARI PWSS | SM/18243 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Topamari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014297) | Assistant Engineer - I | Junior Engineer-02 | ORD/000548/2023-2024 | 2537/MLMD | 04/08/2023 | 27/01/2026 | HANNAN BUILDERS PVT. LTD. | 38.26 | 0 | 0 | 76
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | TOPAMARI PWSS | SM/18243 | New | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for Topamari Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division, PHED.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000383/2024-2025 | 3502/RD/PHE | 02/12/2024 | 01/01/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 15.72 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Islampur | Raiganj Division | TOPAMARI PWSS | SM/18243 | New | Additional pipeline and other ancillary works at Topamari piped water Supply Scheme Under Islampur SubDivision under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000382/2024-2025 | 3501/RD/PHE | 02/12/2024 | 16/01/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 40.29 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Islampur | Malda Mechanical | TOPAMARI PWSS | SM/18243 | New | Quotation for new service connection at TOPAMARI PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18243) |  |  | BILL/01091/2024-2025 | BP-2024-25-262 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 4.38 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Islampur | Raiganj Division | TOPAMARI PWSS | SM/18243 | New | Implementation of TOPAMARI and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd & 3rd Tube Well) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000076/2023-2024 | 2003/RD/PHE | 13/07/2023 | 30/03/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 833.91 | 0 | 0 | 50
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | TOPAMARI PWSS | SM/18243 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Topamari Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000278/2025-2026 | 1797/RD/PHE | 24/06/2025 | 21/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 36.36 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | TOPAMARI PWSS | SM/18243 | New | Construction of Boundary Wall with Gate at Head Work Site, 2nd & 3rd Tube-Well Site under TOPAMARI Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000455/2023-2024 | 563/RD/PHE | 05/03/2024 | 29/05/2025 | MS SANDHYA CONSTRUCTION | 27.69 | 0 | 0 | 95
Total | [13 empty] | 1054.56 | 0 | 0