## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JAGDISHPUR PWSS | SM/18287 | New | Material Requisition To Resource Division |  |  | RTOR000096/2022-2023 | 33/RD/PHE | 06/01/2023 | 06/01/2023 | Resource Division | 115.16 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | JAGDISHPUR PWSS | SM/18287 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Jagdispur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03528/2023-2024 | BP-2023-24-548 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 7.62 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | JAGDISHPUR PWSS | SM/18287 | New | Additional Quotation for Tw-I of Jagadishpur water supply scheme in the district of Uttar Dinajpur. |  |  | BILL/02264/2024-2025 | BP-2024-25-546 | 01/10/2024 | 01/10/2024 | W.B.S.E.D.C.LTD | 0.8 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | JAGDISHPUR PWSS | SM/18287 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Jagadispur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03529/2023-2024 | BP-2023-24-549 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 5.13 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JAGDISHPUR PWSS | SM/18287 | New | Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of Makdampur- Bhatol Road caused due to pipe laying by PHED under Jagadishpur PWSS at different stretched of road under Uttar Dinajpur Highway Division. |  |  | BILL/00307/2024-2025 | BP-2024-25-195 | 18/09/2024 | 18/09/2024 | EXECUTIVE ENGINEER PWD ROADS | 21.58 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JAGDISHPUR PWSS | SM/18287 | New | Implementation of JAGADISHPUR and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000082/2023-2024 | 2001/RD/PHE | 13/07/2023 | 09/01/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 759.23 | 251.06 | 33.07 | 50
7 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | JAGDISHPUR PWSS | SM/18287 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Jagdishpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012027) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000556/2023-2024 | 2507/MLMD | 04/08/2023 | 29/09/2025 | GHOSH BROTHERS... | 36.72 | 0 | 0 | 87
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JAGDISHPUR PWSS | SM/18287 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 17/02/2025 | TECHVISION | 5 | 0 | 0 | 0
Total | [13 empty] | 951.25 | 251.06 | 26.39