## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JAGDISHPUR PWSS | SM/18287 | New | Material Requisition To Resource Division |  |  | RTOR000096/2022-2023 | 33/RD/PHE | 06/01/2023 | 06/01/2023 | Resource Division | 115.16 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | JAGDISHPUR PWSS | SM/18287 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Jagdispur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03528/2023-2024 | BP-2023-24-548 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 7.62 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | JAGDISHPUR PWSS | SM/18287 | New | Additional Quotation for Tw-I of Jagadishpur water supply scheme in the district of Uttar Dinajpur. |  |  | BILL/02264/2024-2025 | BP-2024-25-546 | 01/10/2024 | 01/10/2024 | W.B.S.E.D.C.LTD | 0.8 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | JAGDISHPUR PWSS | SM/18287 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Jagadispur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03529/2023-2024 | BP-2023-24-549 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 5.13 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JAGDISHPUR PWSS | SM/18287 | New | Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of Makdampur- Bhatol Road caused due to pipe laying by PHED under Jagadishpur PWSS at different stretched of road under Uttar Dinajpur Highway Division. |  |  | BILL/00307/2024-2025 | BP-2024-25-195 | 18/09/2024 | 18/09/2024 | EXECUTIVE ENGINEER PWD ROADS | 21.58 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JAGDISHPUR PWSS | SM/18287 | New | Implementation of JAGADISHPUR and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000082/2023-2024 | 2001/RD/PHE | 13/07/2023 | 01/07/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 759.23 | 251.06 | 33.07 | 50
7 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | JAGDISHPUR PWSS | SM/18287 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Jagdishpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012027) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000556/2023-2024 | 2507/MLMD | 04/08/2023 | 27/01/2026 | GHOSH BROTHERS... | 36.72 | 0 | 0 | 87
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JAGDISHPUR PWSS | SM/18287 | New | Construction Of Boundary Wall with Gate at Head Work Site, 2nd & 3rd Tube-Well Site under JAGADISHPUR Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000454/2023-2024 | 562/RD/PHE | 05/03/2024 | 21/05/2024 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 27.71 | 0 | 0 | 100
Total | [13 empty] | 973.97 | 251.06 | 25.78