## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | MACHHALI PWSS | SM/18289 | New | Material Requisition To Resource Division |  |  | RTOR000138/2022-2023 | 723/RD/PHE | 15/03/2023 | 15/03/2023 | Resource Division | 83.09 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | MACHHALI PWSS | SM/18289 | New | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 4(Four) Month (01/03/2024 to 30/06/2024). | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000626/2023-2024 | 472/RD/PHE | 28/02/2024 | 28/06/2024 | PRITAM SARKAR | 1.6 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | MACHHALI PWSS | SM/18289 | New | Quotation for new service connection at MACHHALI PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00244/2024-2025 | BP-2024-25-70 | 15/04/2024 | 15/04/2024 | W.B.S.E.D.C.LTD | 8.34 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | MACHHALI PWSS | SM/18289 | New | Quotation for new service connection at MACHHALI PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00243/2024-2025 | BP-2024-25-69 | 15/04/2024 | 15/04/2024 | W.B.S.E.D.C.LTD | 6.24 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | MACHHALI PWSS | SM/18289 | New | Quotation for new service connection at MACHHALI PH-III (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00626/2024-2025 | BP-2024-25-122 | 24/04/2024 | 24/04/2024 | W.B.S.E.D.C.LTD | 13.65 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | MACHHALI PWSS | SM/18289 | New | Implementation of MACHHALI and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division. (Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rdTubeWell) | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer,Junior Engineer, RWS | ORD/000363/2023-2024 | 2479/RD/PHE | 24/08/2023 | 26/04/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 742.57 | 0 | 0 | 55
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | MACHHALI PWSS | SM/18289 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Machhal PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000452/2024-2025 | 3765/RD/PHED | 18/12/2024 | 01/02/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 75.22 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | MACHHALI PWSS | SM/18289 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under MACHHALI PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000521/2023-2024 | 656/RD/PHE | 05/03/2024 | 12/08/2025 | BIKASH KAR | 27.72 | 0 | 0 | 100
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | MACHHALI PWSS | SM/18289 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Machhali Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000337/2025-2026 | 2487/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 36.37 | 0 | 0 | 0
Total | [13 empty] | 994.79 | 0 | 0