## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. | SM/18290 | Augmentation | Augmentation of ITAHAR Zone-II and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division.PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000079/2023-2024 | 1998/RD/PHE | 13/07/2023 | 26/01/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 639.84 | 17.96 | 2.81 | 10
2 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. | SM/18290 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound yard lighting arrangement at T/W no. I of Augmentation of Itahar Water Supply Scheme(Zone-II) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018223) | Assistant Engineer - I | Junior Engineer-02 | ORD/000597/2023-2024 | 2645/MLMD | 10/08/2023 | 27/05/2026 | M/S TRILOCHAN CONSTRUCTION CO. | 26.7 | 0 | 0 | 72
3 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. | SM/18290 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1189/RD/PHE | 27/04/2023 | 27/04/2023 | Resource Division | 115.81 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. | SM/18290 | Augmentation | Construction Of Approach Road,Laying Of Pipe Line,Fhtc And Other Allied Works Of Itahar Zone - Ii Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000398/2024-2025 | 3567/RD/PHE | 05/12/2024 | 06/03/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 89.77 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. | SM/18290 | Augmentation | Supply, installation and commissioning of electro-mechanical components at T/W No. III of Augmentation of ITAHAR water supply scheme (Zone- II) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001610/2024-2025 | 1691/MLMD | 28/03/2025 | 26/07/2025 | M/S. KUNDU CONSTRACTION | 11.07 | 0 | 0 | 0
Total | [13 empty] | 883.19 | 17.96 | 2.03