## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | TUNIBHITA PWSS | SM/18291 | New | Material Requisition To Resource Division |  |  | RTOR000133/2022-2023 | 637/RD/PHE | 02/03/2023 | 02/03/2023 | Resource Division | 58.92 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | TUNIBHITA PWSS | SM/18291 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Tunibhita Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018453) | Assistant Engineer - I | Junior Engineer-02 | ORD/001816/2023-2024 | 3704/MLMD | 29/11/2023 | 27/05/2026 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 37.34 | 24.74 | 66.25 | 66
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | TUNIBHITA PWSS | SM/18291 | New | Laying of Additional Pipeline with pathway at TUNIBHITA Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte. under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000385/2024-2025 | 3555/RD/PHE | 05/12/2024 | 19/01/2025 | CALCON CONSTRUCTION | 53.07 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | TUNIBHITA PWSS | SM/18291 | New | Quotation for new service connection at TUNIVITA PH-III (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18291) |  |  | BILL/02569/2024-2025 | BP-2024-25-582 | 03/12/2024 | 03/12/2024 | W.B.S.E.D.C.LTD | 17.28 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Raiganj Division | TUNIBHITA PWSS | SM/18291 | New | Implementation of TUNIBHITA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rdTubeWell) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000362/2023-2024 | 2477/RD/PHE | 24/08/2023 | 22/03/2025 | CALCON CONSTRUCTION | 843.51 | 201.96 | 23.94 | 50
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | TUNIBHITA PWSS | SM/18291 | New | Construction of Boundary Wall With Gate at Head Work Site ,2nd &3rd Tube-Well Site under TUNIVITA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000513/2023-2024 | 642/RD/PHE | 05/03/2024 | 04/09/2024 | DULAL DUTTA | 27.71 | 0 | 0 | 100
7 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | TUNIBHITA PWSS | SM/18291 | New | Quotation for new service connection at TUNIBHITA PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18291) |  |  | BILL/02760/2024-2025 | BP-2024-25-626 | 06/02/2025 | 06/02/2025 | W.B.S.E.D.C.LTD | 5.83 | 0 | 0 | 0
Total | [13 empty] | 1043.66 | 226.7 | 21.72