## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DIGHALGAON PWSS | SM/18292 | New | Material Requisition To Resource Division |  |  | RTOR000132/2022-2023 | 639/RD/PHE | 02/03/2023 | 02/03/2023 | Resource Division | 53.73 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DIGHALGAON PWSS | SM/18292 | New | Implementation of DIGHALGAON and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rdTubeWell) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000077/2023-2024 | 2002/RD/PHE | 13/07/2023 | 06/09/2025 | DIPESH BHOWMIK | 503.41 | 53.54 | 10.64 | 40
3 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | DIGHALGAON PWSS | SM/18292 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Dighalgaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018378) | Assistant Engineer - I | Junior Engineer-02 | ORD/000665/2023-2024 | 2745/MLMD | 14/08/2023 | 27/04/2026 | M/S S. S. ENTERPRISE | 38.21 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DIGHALGAON PWSS | SM/18292 | New | Additional pipeline and other ancillary works at Dighalgaon piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000560/2024-2025 | 327/RD/PHE | 17/01/2025 | 17/04/2025 | DIPESH BHOWMIK | 52.29 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DIGHALGAON PWSS | SM/18292 | New | Laying of pipeline with FHTC of DIGHALGAON and it¿s adjoining mouzas Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000566/2023-2024 | 738/RD/PHE | 12/03/2024 | 16/05/2025 | M/S SOMNATH KUNDU | 96.35 | 0 | 0 | 60
6 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | DIGHALGAON PWSS | SM/18292 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-04,Junior Engineer-07 | ORD/001791/2024-2025 | 1276/MLMD | 27/02/2025 | 29/04/2025 | NITAI PANDEY | 0.78 | 0 | 0 | 100
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DIGHALGAON PWSS | SM/18292 | New | Construction of Boundary Wall With Gate at Head Work Site ,2nd &3rd Tube-Well Site under DIGHALGAON PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000546/2023-2024 | 638/RD/PHE | 05/03/2024 | 20/05/2025 | BASU AND COMPANY | 13.85 | 8.61 | 62.13 | 60
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DIGHALGAON PWSS | SM/18292 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd & 3rd Tube-Well Site under DIGHALGAON PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000547/2023-2024 | 639/RD/PHE | 05/03/2024 | 29/05/2025 | M/S UNITED CONTRACTORS | 13.85 | 7.67 | 55.39 | 75
Total | [13 empty] | 772.48 | 69.82 | 9.04