## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DULEPUR PWSS | SM/18293 | New | Material Requisition To Resource Division |  |  | RTOR000131/2022-2023 | 636/RD/PHE | 02/03/2023 | 02/03/2023 | Resource Division | 83.32 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DULEPUR PWSS | SM/18293 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under DULEPUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | ORD/000559/2023-2024 | 660/RD/PHE | 05/03/2024 | 19/04/2024 | BHAGIRATH CONSTRUCTION | 13.86 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DULEPUR PWSS | SM/18293 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under DULEPUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | ORD/000558/2023-2024 | 659/RD/PHE | 05/03/2024 | 19/04/2024 | ANILA CONSTRUCTION | 13.86 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | DULEPUR PWSS | SM/18293 | New | Quotation for new service connection at DULEPUR PH-III (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18293) |  |  | BILL/01517/2024-2025 | BP-2024-25-376 | 18/07/2024 | 18/07/2024 | W.B.S.E.D.C.LTD | 9.99 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | DULEPUR PWSS | SM/18293 | New | Quotation for new service connection at DULEPUR PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18293) |  |  | BILL/01515/2024-2025 | BP-2024-25-374 | 18/07/2024 | 18/07/2024 | W.B.S.E.D.C.LTD | 4.09 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | DULEPUR PWSS | SM/18293 | New | Quotation for new service connection at DULEPUR PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18293) |  |  | BILL/01516/2024-2025 | BP-2024-25-375 | 18/07/2024 | 18/07/2024 | W.B.S.E.D.C.LTD | 10.65 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | DULEPUR PWSS | SM/18293 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Dulepur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018374) | Assistant Engineer - I | Junior Engineer-02 | ORD/000667/2023-2024 | 2746/MLMD | 14/08/2023 | 26/06/2026 | M/S S. S. ENTERPRISE | 37.3 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DULEPUR PWSS | SM/18293 | New | Implementation of DULEPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rdTubeWell) | Assistant Engineer HQ,Assistant Engineer ISD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000361/2023-2024 | 2478/RD/PHE | 24/08/2023 | 01/01/2027 | UTTAM SAHA | 660.02 | 34.7 | 5.26 | 10
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DULEPUR PWSS | SM/18293 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dulepur PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000451/2024-2025 | 3763/RD/PHED | 18/12/2024 | 29/10/2025 | M/S SARKAR ENTERPRISE SILIGURI | 94.92 | 0 | 0 | 30
10 | UTTAR DINAJPUR | Karandighi | Raiganj Division | DULEPUR PWSS | SM/18293 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dulehpur Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000334/2025-2026 | 2485/RD/PHE | 12/09/2025 | 11/03/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 36.38 | 0 | 0 | 0
Total | [13 empty] | 964.38 | 34.7 | 3.6