## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | IKARCHALA PWSS | SM/18294 | New | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 1202/RD/PHE | 28/04/2023 | 28/04/2023 | Resource Division | 58.45 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | IKARCHALA PWSS | SM/18294 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Ikarchala (Zone - II) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014639) | Assistant Engineer - I | Junior Engineer-02 | ORD/000676/2023-2024 | 2696/MLMD | 11/08/2023 | 21/01/2025 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 25.53 | 19.44 | 76.17 | 76
3 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | IKARCHALA PWSS | SM/18294 | New | Quotation for new service connection at IKARCHALA ZONE-II PH-I (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00216/2024-2025 | BP-2024-25-68 | 15/04/2024 | 15/04/2024 | W.B.S.E.D.C.LTD | 12.83 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | IKARCHALA PWSS | SM/18294 | New | Quotation for new service connection at IKARCHALA ZONE-I PH-II (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18294) |  |  | BILL/01100/2024-2025 | BP-2024-25-260 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 4.8 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | IKARCHALA PWSS | SM/18294 | New | Quotation for new service connection at IKARCHALA ZONE-II PH-II (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00215/2024-2025 | BP-2024-25-67 | 15/04/2024 | 15/04/2024 | W.B.S.E.D.C.LTD | 8.19 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | IKARCHALA PWSS | SM/18294 | New | Quotation for new service connection at IKARCHALA ZONE-I PH-I (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18294) |  |  | BILL/01101/2024-2025 | BP-2024-25-261 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 14.56 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | IKARCHALA PWSS | SM/18294 | New | Providing FHTC in connection with Ikarchala Zone-I & II Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000027/2025-2026 | 1180/RD/PHE | 23/04/2025 | 07/06/2025 | HAQUE CONSTRUCTION | 38.77 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | IKARCHALA PWSS | SM/18294 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Ikarchala Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000324/2025-2026 | 1995/RD/PHE | 07/07/2025 | 03/01/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.93 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | IKARCHALA PWSS | SM/18294 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at IKARCHALA ZONE-I PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000390/2025-2026 | 2044/RD/PHE | 09/07/2025 | 05/01/2026 | GANGARAMPUR UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.29 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | IKARCHALA PWSS | SM/18294 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at IKARCHALA ZONE-II PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000256/2025-2026 | 2046/RD/PHE | 10/07/2025 | 06/01/2026 | ROY ENGINEERS. (PATNA) | 32.95 | 0 | 0 | 0
Total | [13 empty] | 259.29 | 19.44 | 7.5