## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. | SM/18295 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1188/RD/PHE | 27/04/2023 | 27/04/2023 | Resource Division | 288.75 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. | SM/18295 | Augmentation | Augmentation of ITAHAR Zone-I and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division,PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD | ORD/000078/2023-2024 | 1997/RD/PHE | 13/07/2023 | 01/05/2025 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 568.17 | 0 | 0 | 30
3 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. | SM/18295 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound yard lighting arrangement at T/W no. I of Augmentation of Itahar Water Supply Scheme(Zone-I) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018165) | Assistant Engineer - I | Junior Engineer-02 | ORD/000595/2023-2024 | 2644/MLMD | 10/08/2023 | 28/11/2025 | JIBU SINGHA | 26.96 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. | SM/18295 | Augmentation | Construction Of Approach Road, Laying of Pipe Line,Retaining And Other Allied Works Of Itahar Zone -I Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000397/2024-2025 | 3566/RD/PHE | 05/12/2024 | 06/03/2025 | AJIT PRAMANIK | 95.62 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. | SM/18295 | Augmentation | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000412/2024-2025 | 3446/RD/PHE | 26/11/2024 | 26/05/2025 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. | SM/18295 | Augmentation | Supply, installation and commissioning of electro-mechanical components at T/W No. III of Augmentation of ITAHAR water supply scheme (Zone- I) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001611/2024-2025 | 1692/MLMD | 28/03/2025 | 26/07/2025 | DAS CONSTRUCTION | 11.06 | 0 | 0 | 0
Total | [13 empty] | 992.97 | 0 | 0