## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Raiganj Division | GUNJARIA PWSS | SM/18296 | New | Material Requisition To Resource Division |  |  | RTOR000120/2022-2023 | 618/RD/PHE | 28/02/2023 | 28/02/2023 | Resource Division | 83.71 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Islampur | Raiganj Division | GUNJARIA PWSS | SM/18296 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under GUNJARIA PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | ORD/000520/2023-2024 | 653/RD/PHE | 05/03/2024 | 19/04/2024 | M/S LUCKY CONSTRUCTION | 24.49 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | GUNJARIA PWSS | SM/18296 | New | Implementation of GUNJARIA and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000213/2023-2024 | 2296/RD/PHE | 04/08/2023 | 28/04/2026 | UTTAM SAHA | 631.56 | 140.14 | 22.19 | 40
4 | UTTAR DINAJPUR | Islampur | Malda Mechanical | GUNJARIA PWSS | SM/18296 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Gunjaria Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/016520) | Assistant Engineer - I | Junior Engineer-02 | ORD/000591/2023-2024 | 2640/MLMD | 10/08/2023 | 26/06/2026 | JAL PRAVAHIKA PVT. LTD. | 29.41 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Islampur | Raiganj Division | GUNJARIA PWSS | SM/18296 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Gunjaria Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000285/2025-2026 | 1807/RD/PHE | 24/06/2025 | 21/12/2025 | AJIT PRAMANIK | 33.6 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Islampur | Malda Mechanical | GUNJARIA PWSS | SM/18296 | New | Quotation for new service connection at GUNJARIA PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18296) |  |  | BILL/02762/2024-2025 | BP-2024-25-625 | 06/02/2025 | 06/02/2025 | W.B.S.E.D.C.LTD | 10.56 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | GUNJARIA PWSS | SM/18296 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000411/2024-2025 | 1816/RD/PHE | 26/06/2024 | 10/01/2025 | MD ZAFAR EQUEBAL | 2.6 | 0 | 0 | 100
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | GUNJARIA PWSS | SM/18296 | New | Providing FHTC in connection with Gunjaria Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000511/2024-2025 | 56/RD/PHE | 03/01/2025 | 03/04/2025 | M/S. B. PAUL & COMPANY | 13.85 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Islampur | Raiganj Division | GUNJARIA PWSS | SM/18296 | New | Additional pipeline and other ancillary works with path way and earth filling at Gunjaria piped water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000253/2025-2026 | 1487/RD/PHE | 04/06/2025 | 19/07/2025 | M/S LUCKY CONSTRUCTION | 62.34 | 0 | 0 | 0
Total | [13 empty] | 892.11 | 140.14 | 15.71