## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/18298 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 0 | 0 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/18298 | New | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 2245/RD/PHE | 02/08/2023 | 02/08/2023 | Resource Division | 30.75 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/18298 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DHOARAI (Zone-I)PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000523/2023-2024 | 672/RD/PHE | 05/03/2024 | 30/11/2024 | D. K. ASSOCIATES | 22.58 | 0 | 0 | 100
4 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/18298 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Dhoarai (Zone-I), Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03660/2023-2024 | BP-2023-24-628 | 06/03/2024 | 06/03/2024 | W.B.S.E.D.C.LTD | 0.45 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/18298 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dhoarai (Zone-I), Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03661/2023-2024 | BP-2023-24-629 | 06/03/2024 | 06/03/2024 | W.B.S.E.D.C.LTD | 0.55 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/18298 | New | Implementation of DHOARAI ZONE-I and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000080/2023-2024 | 1999/RD/PHE | 13/07/2023 | 01/01/2026 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 476.5 | 0 | 0 | 50
7 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/18298 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite at T/W no. I of Dhoarai Zone-I Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017842) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000479/2023-2024 | 2487/MLMD | 04/08/2023 | 28/03/2026 | M/S TRILOCHAN CONSTRUCTION CO. | 25.16 | 0 | 0 | 85
8 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/18298 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dhoarai Zone-1 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000488/2024-2025 | 21/RD/PHE | 02/01/2025 | 16/02/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 51.46 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/18298 | New | Trial Run For Dharai Zone-II PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000730/2024-2025 | 529/RD/PHE | 12/02/2025 | 13/05/2025 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. | 0.82 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/18298 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dhoaroi Zone-I Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist:Uttar Dinajpur, Block: Raiganj,Capacity- 60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000262/2025-2026 | 1627/RD/PHE | 19/06/2025 | 16/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.58 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/18298 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0 | 0 | 100
Total | [13 empty] | 705.87 | 0 | 0