## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Malda Mechanical | DOHASO PWSS | SM/18304 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Dohaso, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001512/2023-2024 | 4003216769 | 24/08/2023 | 22/11/2023 | W.B.S.E.D.C.LTD | 9.76 | 9.76 | 100 | 100
2 | UTTAR DINAJPUR | Islampur | Raiganj Division | DOHASO PWSS | SM/18304 | New | Material Requisition To Resource Division |  |  | RTOR000108/2022-2023 | 605/RD/PHE | 27/02/2023 | 27/02/2023 | Resource Division | 93.61 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | DOHASO PWSS | SM/18304 | New | ADDITIONAL LAYING OF UPVC PIPE LINE with anciliary works at DOHASO PWSS WITHIN ISLAMPUR BLOCK UNDER RAIGANJ DIVISION P.H.E. DTE., RAIGANJ, UTTAR DINAJPUR. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000361/2024-2025 | 3480/RD/PHE | 02/12/2024 | 16/01/2025 | AJIT PRAMANIK | 81.53 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Islampur | Malda Mechanical | DOHASO PWSS | SM/18304 | New | Quotation for new service connection at DOHASO PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00027/2024-2025 | BP-2024-25-37 | 08/04/2024 | 08/04/2024 | W.B.S.E.D.C.LTD | 8.77 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Islampur | Malda Mechanical | DOHASO PWSS | SM/18304 | New | Quotation for new service connection at DOHASO PH-III (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00028/2024-2025 | BP-2024-25-38 | 08/04/2024 | 08/04/2024 | W.B.S.E.D.C.LTD | 7.61 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Islampur | Raiganj Division | DOHASO PWSS | SM/18304 | New | Implementation of DOHASO and its adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000165/2023-2024 | 2091/RD/PHE | 27/07/2023 | 01/01/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 1441.52 | 795.41 | 55.18 | 60
7 | UTTAR DINAJPUR | Islampur | Malda Mechanical | DOHASO PWSS | SM/18304 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Dohaso Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015576) | Assistant Engineer - I | Junior Engineer-02 | ORD/000495/2023-2024 | 2495/MLMD | 04/08/2023 | 26/06/2026 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD.. | 42.58 | 0 | 0 | 58
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | DOHASO PWSS | SM/18304 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under DOHASO PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000541/2023-2024 | 609/RD/PHE | 05/03/2024 | 16/10/2024 | DIPAK SAHA | 13.85 | 0 | 0 | 100
9 | UTTAR DINAJPUR | Islampur | Raiganj Division | DOHASO PWSS | SM/18304 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under DOHASO PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000542/2023-2024 | 610/RD/PHE | 05/03/2024 | 16/10/2024 | M/S ANTARA | 13.85 | 0 | 0 | 100
Total | [13 empty] | 1713.1 | 805.18 | 47