## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/18341 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer RSD |  | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 04/10/2022 | RADIANT | 47.87 | 13.83 | 28.89 | 100
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/18341 | New | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 2244/RD/PHE | 02/08/2023 | 02/08/2023 | Resource Division | 123.16 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/18341 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no.I,II, III & IV and Making compound yard lighting arrangement and Grid connected ground mounted solar PV system with net metering at T/W no.- I of Kapasia Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016713) | Assistant Engineer - I | Junior Engineer-02 | ORD/000610/2023-2024 | 2653/MLMD | 10/08/2023 | 04/02/2029 | DEY ENTERPRISE.. | 59.26 | 41.43 | 69.92 | 72
4 | UTTAR DINAJPUR | Itahar | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/18341 | New | Implementation of KAPASIA and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD | ORD/000166/2023-2024 | 2092/RD/PHE | 27/07/2023 | 17/05/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 1262.96 | 213.79 | 16.93 | 30
5 | UTTAR DINAJPUR | Itahar | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/18341 | New | Construction of Approach Road, Laying of Pipe Line, FHTC And Other Allied Works of Kapasia PWSS Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000389/2024-2025 | 3559/RD/PHE | 05/12/2024 | 06/03/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 48.29 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Itahar | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/18341 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd, 3rd & 4th Tube-Well Site under KAPASIA PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000498/2023-2024 | 621/RD/PHE | 05/03/2024 | 06/02/2025 | KRISHNA CONSTRUCTION | 35.63 | 0 | 0 | 50
7 | UTTAR DINAJPUR | Itahar | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/18341 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12 months (Period from 17.10.2023 to 16.10.2024) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000627/2023-2024 | 2876/RD/PHE | 17/10/2023 | 17/10/2024 | ARNAB DUTTA | 4.8 | 1.18 | 24.67 | 100
8 | UTTAR DINAJPUR | Itahar | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/18341 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kapasia Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 150 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000343/2025-2026 | 2491/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 52.01 | 0 | 0 | 0
Total | [13 empty] | 1633.97 | 270.23 | 16.54