## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Raiganj Division | PURBBA GOMAIDIGHI PWSS | SM/18448 | New | Implementation of PURBA GOMAIDIGHI and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000344/2023-2024 | 2470/RD/PHE | 24/08/2023 | 01/01/2026 | PRADIP KUMAR PAUL | 692.96 | 303.91 | 43.86 | 75
2 | UTTAR DINAJPUR | Islampur | Raiganj Division | PURBBA GOMAIDIGHI PWSS | SM/18448 | New | Material Requisition To Resource Division |  |  | RTOR000122/2022-2023 | 619/RD/PHE | 28/02/2023 | 28/02/2023 | Resource Division | 41.78 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | PURBBA GOMAIDIGHI PWSS | SM/18448 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under PURBA GUMAIDIGHI PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000525/2023-2024 | 546/RD/PHE | 05/03/2024 | 19/04/2024 | M/S BABA LOKNATH CONSTRUCTION | 22.57 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Islampur | Raiganj Division | PURBBA GOMAIDIGHI PWSS | SM/18448 | New | Laying of Additional pipeline with other ancillary works at different mouzas of PURBA GOMAIDIGHI PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000374/2024-2025 | 3493/RD/PHE | 02/12/2024 | 11/01/2026 | PRADIP KUMAR PAUL | 78.28 | 0 | 0 | 40
5 | UTTAR DINAJPUR | Islampur | Malda Mechanical | PURBBA GOMAIDIGHI PWSS | SM/18448 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no.I & II and making compound lighting arrangement at T/W no.I of PURBA GOMAIDIGHI Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/002577/2023-2024 | 1003/MLMD | 11/03/2024 | 26/06/2026 | DEY ENTERPRISE.. | 28.11 | 20.79 | 73.97 | 79
6 | UTTAR DINAJPUR | Islampur | Malda Mechanical | PURBBA GOMAIDIGHI PWSS | SM/18448 | New | Quotation for new service connection at PURBBA GOMAIDIGHI PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00225/2024-2025 | BP-2024-25-66 | 15/04/2024 | 15/04/2024 | W.B.S.E.D.C.LTD | 10.07 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Malda Mechanical | PURBBA GOMAIDIGHI PWSS | SM/18448 | New | Quotation for new service connection at PURBBA GOMAIDIGHI PH-II (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00217/2024-2025 | BP-2024-25-65 | 15/04/2024 | 15/04/2024 | W.B.S.E.D.C.LTD | 10.53 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | PURBBA GOMAIDIGHI PWSS | SM/18448 | New | Construction of Road restoration with dismantling and approach road in connection with the New Scheme of Purba Gomaidighi PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000245/2025-2026 | 1465/RD/PHE | 04/06/2025 | 04/07/2025 | SHIB LOKNATH ENTERPRISE | 23.9 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Islampur | Raiganj Division | PURBBA GOMAIDIGHI PWSS | SM/18448 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Purba Gomaidighi Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000288/2025-2026 | 1810/RD/PHE | 24/06/2025 | 21/12/2025 | PRADIP KUMAR PAUL | 19.12 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Islampur | Malda Mechanical | PURBBA GOMAIDIGHI PWSS | SM/18448 | New | Additional Quotation for new service connection at Purbba Gomaidighi (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18448) |  |  | BILL/01263/2026-2027 |  | 13/08/2026 | 13/08/2026 | W.B.S.E.D.C.LTD | 6.83 | 0 | 0 | 0
Total | [13 empty] | 934.15 | 324.7 | 34.76