## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Malda Mechanical | ILLUABARI PWSS | SM/18449 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Iluabari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018454) |  |  | ORD/001812/2023-2024 | 3699/MLMD | 29/11/2023 | 27/05/2024 | SHREE BISHNU CONSTRUCTION | 27.45 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Islampur | Raiganj Division | ILLUABARI PWSS | SM/18449 | New | Material Requisition To Resource Division |  |  | RTOR000111/2022-2023 | 604/RD/PHE | 27/02/2023 | 27/02/2023 | Resource Division | 35.46 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Islampur | Malda Mechanical | ILLUABARI PWSS | SM/18449 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Iluabari (Zone-I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018454) | Assistant Engineer - I | Junior Engineer-02 | ORD/000678/2023-2024 | 2697/MLMD | 11/08/2023 | 26/06/2026 | KAMAKHYA ENTERPRISE. | 27.18 | 0 | 0 | 82
4 | UTTAR DINAJPUR | Islampur | Malda Mechanical | ILLUABARI PWSS | SM/18449 | New | Quotation for new service connection at ILLUABARI PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18449) |  |  | BILL/00736/2024-2025 | BP-2024-25-180 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 12.28 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Islampur | Malda Mechanical | ILLUABARI PWSS | SM/18449 | New | Quotation for new service connection at ILLUABARI PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18449) |  |  | BILL/00735/2024-2025 | BP-2024-25-179 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 8.84 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Islampur | Malda Mechanical | ILLUABARI PWSS | SM/18449 | New | Quotation for new service connection at ILLUABARI ZONE-II PH-II (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18449) |  |  | BILL/02082/2024-2025 | BP-2024-25-481 | 09/09/2024 | 09/09/2024 | W.B.S.E.D.C.LTD | 3.64 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Malda Mechanical | ILLUABARI PWSS | SM/18449 | New | Quotation for new service connection at ILLUABARI ZONE-II PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18449) |  |  | BILL/02081/2024-2025 | BP-2024-25-480 | 09/09/2024 | 09/09/2024 | W.B.S.E.D.C.LTD | 5.89 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | ILLUABARI PWSS | SM/18449 | New | Implementation of ILUABARI (Zone-I & Zone-II) and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000214/2023-2024 | 2301/RD/PHE | 04/08/2023 | 01/01/2026 | M/S. B. PAUL & COMPANY | 1194.94 | 0 | 0 | 60
9 | UTTAR DINAJPUR | Islampur | Raiganj Division | ILLUABARI PWSS | SM/18449 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under ILUABARI PWSS (ZONE-I) & ILUABARI PWSS (ZONE-II) at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000512/2023-2024 | 637/RD/PHE | 05/03/2024 | 13/05/2025 | M/S. B. PAUL & COMPANY | 47.94 | 0 | 0 | 85
10 | UTTAR DINAJPUR | Islampur | Raiganj Division | ILLUABARI PWSS | SM/18449 | New | Laying additional pipe line,Road Restoration and Approach Road in connection with New Scheme Of Iluabari Zone-I and Zone-II Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer,Junior Engineer, ISD | ORD/000415/2024-2025 | 3579/RD/PHE | 05/12/2024 | 14/01/2026 | M/S. B. PAUL & COMPANY | 97.01 | 0 | 0 | 20
11 | UTTAR DINAJPUR | Islampur | Raiganj Division | ILLUABARI PWSS | SM/18449 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Iluabari Zone-I & Zone-II Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 120 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000328/2025-2026 | 2013/RD/PHE | 08/07/2025 | 04/01/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 59.18 | 0 | 0 | 0
Total | [13 empty] | 1519.8 | 0 | 0