## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Preparation of DPR for drinking water supply scheme to facilitate 4(Four)Nos. Augmentation Scheme and 1(One) No. New PWSS (List Enclosed) Uncovered mouzas under Uttar Dinajpur District which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000201/2023-2024 | 2226/RD/PHE | 31/07/2023 | 15/08/2023 | RADIANT | 11.57 | 6.91 | 59.69 | 100
2 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 2259/RD/PHE | 03/08/2023 | 03/08/2023 | Resource Division | 141.14 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 10.06.2024 to 14.06.2024. |  |  | BILL/00128/2024-2025 | BP-2024-25-93 | 28/06/2024 | 28/06/2024 | M/S DILWAR HOSAIN | 0.08 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 13.05.2024 to 17.05.2024. |  |  | BILL/00129/2024-2025 | BP-2024-25-94 | 28/06/2024 | 28/06/2024 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Beldangi Road from 7.00 km to 9.40 km under Dakshin Dinajpur Highway Division in the District of Dakshin Dinajpur, Urgent restoration of Hard Shoulder in stretches caused due to laying of pipeline by PHED under Chhayghara PWSS under Raiganj Divison, PHE Dte. |  |  | BILL/00494/2024-2025 | BP-2024-25-281 | 05/11/2024 | 05/11/2024 | EXECUTIVE ENGINEER (DAKSHIN DINAJPUR HIGHWAY DIVISION) | 11.19 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 03.09.2024 and 09.09.2024. |  |  | BILL/00383/2024-2025 | BP-2024-25-223 | 04/10/2024 | 04/10/2024 | SAHA CONSTRUCTION | 0.07 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no- I & II of Chhayghara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018690) | Assistant Engineer - I | Junior Engineer-02 | ORD/000654/2023-2024 | 2741/MLMD | 14/08/2023 | 27/07/2026 | MAA BHABOTARINE ENTERPRISE. | 24.24 | 5.36 | 22.13 | 84
8 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Construction Of Approach Road,Laying Of Pipe Line,Fhtc And Other Allied Works Of Chayaghara Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000399/2024-2025 | 3568/RD/PHE | 05/12/2024 | 06/03/2025 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 52.27 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Construction of Boundary Wall With Gate at Head Work Site ,2nd &3rd Tube-Well Site under CHHAYGHARA PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ | ORD/000508/2023-2024 | 633/RD/PHE | 05/03/2024 | 28/02/2025 | PRIMECON ENTERPRISE | 27.71 | 0 | 0 | 60
10 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12 months (Period from 17.10.2023 to 16.10.2024) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000627/2023-2024 | 2876/RD/PHE | 17/10/2023 | 17/10/2024 | ARNAB DUTTA | 4.8 | 1.18 | 24.49 | 100
11 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chhayghora Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000315/2025-2026 | 2478/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 19.35 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Work Order for hiring charges of vehicle with fuel, hired for site works for RWS Raiganj Sub-Division under Raiganj Division, P.H.E. Dte. for the period from 09.09.2024 to 13.09.2024. |  |  | BILL/00697/2024-2025 | BP-2024-25-420 | 27/03/2025 | 27/03/2025 | M/S SARKAR ENTERPRISE SILIGURI | 0.09 | 0 | 0 | 0
13 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Work Order for hiring charges of vehicle with fuel, hired for site works for RWS Raiganj Sub-Division under Raiganj Division, P.H.E. Dte. for the period from 02.09.2024 to 06.09.2024. |  |  | BILL/00698/2024-2025 | BP-2024-25-421 | 27/03/2025 | 27/03/2025 | M/S SARKAR ENTERPRISE SILIGURI | 0.09 | 0 | 0 | 0
14 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Quotation for new service connection at CHHAYGHARA PH-I (Itahar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18450) |  |  | BILL/02723/2024-2025 | BP-2024-25-585 | 10/12/2024 | 10/12/2024 | W.B.S.E.D.C.LTD | 9.2 | 0 | 0 | 0
15 | UTTAR DINAJPUR | Itahar | Malda Mechanical | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Quotation for new service connection at CHHAYGHARA PH-II (Itahar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18450) |  |  | BILL/02973/2024-2025 |  | 23/12/2024 | 23/12/2024 | W.B.S.E.D.C.LTD | 24.21 | 0 | 0 | 0
16 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Implementation of CHHAYGHARA and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000345/2023-2024 | 2471/RD/PHE | 24/08/2023 | 19/12/2025 | M/S S.D. ENTERPRISE | 775.32 | 207.62 | 26.78 | 40
17 | UTTAR DINAJPUR | Itahar | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | SM/18450 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59C 0644) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 01/07/2024 to 14/01/2025. | Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RWS | ORD/000407/2024-2025 | 1980/RD/PHE | 29/06/2024 | 13/01/2025 | PRITAM SARKAR | 2.6 | 0.4 | 15.36 | 100
Total | [13 empty] | 1104.01 | 221.46 | 20.06