## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD |  | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 26/09/2022 | RADIANT | 63.04 | 8.22 | 13.04 | 100
2 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Implementation of KALUA and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000164/2023-2024 | 2090/RD/PHE | 27/07/2023 | 12/04/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 798.98 | 257 | 32.17 | 56
3 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II,III,IV & V and making compound lighting arrangement ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Kalua Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018393) | Assistant Engineer - I | Junior Engineer-07 | ORD/000675/2023-2024 | 2754/MLMD | 14/08/2023 | 08/02/2029 | DILIP MAHATO. | 67.92 | 0 | 0 | 77
4 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Kalua,PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001961/2023-2024 | 4003279144 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 4.53 | 4.53 | 100 | 100
5 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Kalua,PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001962/2023-2024 | 4003279164 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 12.79 | 12.79 | 100 | 100
6 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 2243/RD/PHE | 02/08/2023 | 02/08/2023 | Resource Division | 99.68 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Construction of Boundary Wall With Gate at Head Work, 2nd, 3rd, 4th & 5th Tube-Well Site under KALUA PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2023-2024 | 651/RD/PHE | 05/03/2024 | 28/02/2025 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 37.97 | 0 | 0 | 80
8 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site, 2nd & 3rd tubewell site and road restoration of Kalua PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000434/2024-2025 | 3747/RD/PHE | 18/12/2024 | 02/05/2025 | AJIT PRAMANIK | 84.29 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0.4 | 8.06 | 100
10 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Kalua, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03636/2023-2024 | BP-2023-24-620 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.LTD | 6.78 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Hemtabad | Malda Mechanical | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Additional quotation of Kalua PWSS TW-III in the district of Uttar Dinajpur. |  |  | BILL/01790/2024-2025 | BP-2024-25-437 | 20/08/2024 | 20/08/2024 | W.B.S.E.D.C.LTD | 3.7 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 12/02/2026 | TECHVISION | 5 | 0 | 0 | 83
13 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kalua Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity- 150 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000303/2025-2026 | 2472/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 52.02 | 0 | 0 | 0
14 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 02.02.2024 and 05.02.2024 to 08.02.2024. |  |  | BILL/00615/2024-2025 | BP-2024-25-316 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.06 | 0 | 0 | 0
15 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 22.02.2024 to 23.02.2024 and 27.02.2024 to 29.02.2024. |  |  | BILL/00617/2024-2025 | BP-2024-25-318 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.06 | 0 | 0 | 0
16 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 25.01.2024 and 29.01.2024 to 31.01.2024. |  |  | BILL/00614/2024-2025 | BP-2024-25-315 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.07 | 0 | 0 | 0
17 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 12.02.2024, 15.02.2024 to 16.02.2024 and 19.02.2024 to 20.02.2024. |  |  | BILL/00616/2024-2025 | BP-2024-25-317 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.06 | 0 | 0 | 0
18 | UTTAR DINAJPUR | Hemtabad | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 17.01.2024 to 19.01.2024 and 22.01.2024. |  |  | BILL/00613/2024-2025 | BP-2024-25-314 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.04 | 0 | 0 | 0
Total | [13 empty] | 1241.96 | 282.95 | 22.78