## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | UTTAR SHAHAPUR PWSS | SM/18475 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Uttar Sahapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016451) | Assistant Engineer - I | Junior Engineer-02 | ORD/000549/2023-2024 | 2538/MLMD | 04/08/2023 | 24/09/2026 | HANNAN BUILDERS PVT. LTD. | 39.82 | 30.76 | 77.24 | 77
2 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | UTTAR SHAHAPUR PWSS | SM/18475 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | JUNIOR ENGINEER,Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 26/08/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 377.61 | 2.92 | 35
3 | UTTAR DINAJPUR | Goalpokhar-II | Raiganj Division | UTTAR SHAHAPUR PWSS | SM/18475 | New | Material Requisition To Resource Division |  |  | RTOR000182/2022-2023 | 982/RD/PHE | 30/03/2023 | 30/03/2023 | Resource Division | 66.81 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | UTTAR SHAHAPUR PWSS | SM/18475 | New | Quotation for new service connection at UTTAR SHAHAPUR PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18475) |  |  | BILL/01098/2024-2025 | BP-2024-25-258 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 6.85 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | UTTAR SHAHAPUR PWSS | SM/18475 | New | Quotation for new service connection at UTTAR SHAHAPUR PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18475) |  |  | BILL/01099/2024-2025 | BP-2024-25-259 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 8.3 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Goalpokhar-II | Malda Mechanical | UTTAR SHAHAPUR PWSS | SM/18475 | New | Quotation for new service connection at UTTAR SHAHAPUR PH-III (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18475) |  |  | BILL/01097/2024-2025 | BP-2024-25-257 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 6.18 | 0 | 0 | 0
Total | [13 empty] | 13059.03 | 408.37 | 3.13