## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JHITKAI PWSS | SM/18476 | New | Material Requisition To Resource Division |  |  | RTOR000153/2022-2023 | 1052/RD/PHE | 06/04/2023 | 06/04/2023 | Resource Division | 74.65 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | JHITKAI PWSS | SM/18476 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Jhitkai, Birnagar CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03544/2023-2024 | BP-2023-24-571 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 3.2 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | JHITKAI PWSS | SM/18476 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Jhitkai, Birnagar CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/01614/2024-2025 | BP-2024-25-396 | 29/07/2024 | 29/07/2024 | W.B.S.E.D.C.LTD | 13.84 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JHITKAI PWSS | SM/18476 | New | Wayleave/ track crossing proposal with application ID : NFR-KIR-2024-WL-11 under Katihar Division of Northeast Frontier Railway in connection with Jhitkai PWSS in Raiganj Block under Raiganj Division PHE Dte. |  |  | BILL/00100/2024-2025 | BP-2024-25-69 | 06/06/2024 | 06/06/2024 | EXECUTIVE ENGINEER | 0.11 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JHITKAI PWSS | SM/18476 | New | Way leave/track crossing proposal with application id: NFR-KIR-2024-WL-11 under Kathihar Division of North East Fronter Railway in connection with Jhitkia PWSS in Raiganj Block under Raiganj Division, PHE Dte. |  |  | BILL/00158/2024-2025 | BP-2024-25-104 | 09/07/2024 | 09/07/2024 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 6.13 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JHITKAI PWSS | SM/18476 | New | Implementation of JHITKAI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000211/2023-2024 | 2294/RD/PHE | 04/08/2023 | 20/04/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 751.51 | 278.74 | 37.09 | 50
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JHITKAI PWSS | SM/18476 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Jhitkia, 2.Bhomra in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000225/2023-2024 | 2366/RD/PHE | 11/08/2023 | 01/02/2025 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 24.57 | 30.87 | 100
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JHITKAI PWSS | SM/18476 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site, 2nd & 3rd tubewell site and road restoration of Jhitkai PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000430/2024-2025 | 3742/RD/PHE | 18/12/2024 | 02/05/2025 | BHOLA PAUL | 29.79 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | JHITKAI PWSS | SM/18476 | New | Jack Pushing of M.S. Pipe of 200 mm dia. Through 600 mm dia. M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 14/2 to 14/3 near Jhitkai Railway Station (JTK) for Jhitkai and it's adjoining mouzas water supply scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur . | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000139/2024-2025 | 2834/RD/PHE | 23/09/2024 | 01/03/2025 | M/S TRILOCHAN CONSTRUCTION CO | 30.18 | 0 | 0 | 100
Total | [13 empty] | 989.01 | 303.31 | 30.67