## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Balia Piped Water Supply Scheme. | SM/18493 | New | Material Requisition To Resource Division |  |  | RTOR000134/2022-2023 | 654/RD/PHE | 03/03/2023 | 03/03/2023 | Resource Division | 33.83 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Balia Piped Water Supply Scheme. | SM/18493 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) BALIA in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RWS | ORD/000224/2023-2024 | 2365/RD/PHE | 11/08/2023 | 25/09/2023 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 17.79 | 0 | 0 | 100
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Balia Piped Water Supply Scheme. | SM/18493 | New | Additional Quotation for p/h-I of Balia PWSS in the district of Uttar Dinajpur. |  |  | BILL/02202/2024-2025 | BP-2024-25-522 | 26/09/2024 | 26/09/2024 | W.B.S.E.D.C.LTD | 4.76 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Balia Piped Water Supply Scheme. | SM/18493 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Balia, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/01053/2024-2025 | BP-2024-25-237 | 29/05/2024 | 29/05/2024 | W.B.S.E.D.C.LTD | 3.95 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Balia Piped Water Supply Scheme. | SM/18493 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Balia, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/01054/2024-2025 | BP-2024-25-238 | 29/05/2024 | 29/05/2024 | W.B.S.E.D.C.LTD | 1.95 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Balia Piped Water Supply Scheme. | SM/18493 | New | Additional Quotation for p/h-II of Balia PWSS in the district of Uttar Dinajpur. |  |  | BILL/02201/2024-2025 | BP-2024-25-521 | 26/09/2024 | 26/09/2024 | W.B.S.E.D.C.LTD | 1.93 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | Balia Piped Water Supply Scheme. | SM/18493 | New | Implementation of BALIA and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000212/2023-2024 | 2295/RD/PHE | 04/08/2023 | 22/10/2025 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 578.22 | 0 | 0 | 40
8 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | Balia Piped Water Supply Scheme. | SM/18493 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II of Balia Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/004007) | Assistant Engineer - I | Junior Engineer-07 | ORD/000397/2023-2024 | 2437/MLMD | 04/08/2023 | 01/06/2025 | SOUNAK ENTERPRISE | 22.21 | 0 | 0 | 100
Total | [13 empty] | 664.63 | 0 | 0